## KAK
No | Sub | Usecase | Jenis | Catatan | Catatan | Unadjusted Use Case Weighting (UUCW) | [7 empty] | Unadjusted Actor Weight (UAW)
[6 empty] | Jumlah UI | Kompleksitas Use Case | Bobot UUCW | UUCW |  |  |  |  | Aktor | Jenis Aktor | UAW
1 | Portal | Penerbitan Nopen | CRUD |  |  | 1 | Average | 10 | 10 |  |  |  |  | Pengguana Jasa | Complex | 3 | Unadjusted Actor Weight (UAW)
2 |  | Home - Tampilan umum icon (Knowledgebase, News & Event, Layanan, Buat Tiket) | Read |  |  | 1 | Average | 10 | 10 |  |  |  |  | Analis | Complex | 3 | Actor Classification | Type of Actor | Weight
3 |  | Knowledgebase (Pencarian, User manual, FAQ, Publikasi, Form Request) | Read |  |  | 1 | Average | 10 | 10 |  |  |  |  | Admin IKC | Complex | 3 | Simple | Berinteraksi melalui API, seperti Command Prompt | 1
4 |  | News & Event - tampilan berita dan acara IKC, dapat diganti sesuai kebutuhan admin portal | Read |  |  | 1 | Average | 10 | 10 |  |  |  |  | Technical Support | Complex | 3 | Average | Berinteraksi melalui Protokol, seperti TCP/IP | 2
5 |  | Perekaman Layanan Service Katalog | CRUD |  |  | 1 | Complex | 15 | 15 |  |  |  |  | Pegawai IKC | Average | 2 | Complex | Berinteraksi melalui GUI atau Web Page | 3
6 |  | Melihat status layanan | Read |  |  | 1 | Average | 10 | 10 |  |  |  |  | Seksi DIKC | Simple | 1
7 | Inhouse | CMS Knowledge, News & Event | CRUD |  |  | 2 | Complex | 15 | 30 |  |  |  |  | Subdit DIKC | Simple | 1
8 |  | Manajemen release | CRUD |  |  | 2 | Complex | 15 | 30 |  |  |  |  | TOTAL | 0 | 15 | Use Case Clasification Weight (UUCW)
9 |  | Perekaman Issue | CRUD |  |  | 2 | Complex | 15 | 30 | 450 | 13500 | 6075000 | 82012500000 |  |  |  | Tipe Usecase | No. of Transactions | Bobot
10 |  | Manajemen layanan Service Katalog | CRUD |  |  | 4 | Complex | 15 | 60 |  |  |  |  | Unadjusted Use Case Points (UUCP=Tot UUCW+Tot UAW)
|  | Tindak Lanjut layanan Service Katalog | CRUD |  |  | 1 | Average | 10 | 10
11 |  | Manajemen distribusi ticket | CRUD |  |  | 1 | Average | 10 | 10 |  |  |  |  | 310 |  |  | Simple | Menggunakan ≤ 3 transaksi | 5
|  | Browse | Read |  |  | 2 | Simple | 5 | 10
12 |  | Setting | CRUD |  |  | 4 | Simple | 5 | 20 | [7 empty] | Average | Menggunakan 4 - 7 transaksi | 10
13 | Dashboard | Menampilkan statistik gangguan | Read |  |  | 2 | Average | 10 | 20 | [7 empty] | Complex | Lebih dari 7 transaksi | 15
14 |  | Menampilkan performa petugas | Read |  |  | 1 | Simple | 5 | 5
15 |  | Menampilkan monitoring SLA | Read |  |  | 1 | Simple | 5 | 5
TOTAL | [8 empty] | 295 | #REF! | #REF! | #REF! | #REF!

## TCF - EF
Technical Complexity Factor | Weight | Relevance 0-5 | Score | Keterangan
T1 Distributed System | 2 | 0 | 0 | Sistem tersentralisasi
T2 Performance | 1 | 3 | 3 | Kecepatan akses baik
T3 End User Efficiency | 1 | 2 | 2 | Web based, pengaruh spesifikasi user
T4 Complex Internal Processing | 1 | 3 | 3 | Complex
T5 Reusability | 1 | 2 | 2 | Component Based
T6 Easy to Install | 0.5 | 3 | 1.5 | Container based deployment
T7 Easy to Use | 0.5 | 4 | 2 | Web Based
T8 Portability | 2 | 2 | 4 | Backend dapat digunakan oleh sistem lainnya
T9 Easy to Change | 1 | 2 | 2 | Penyesuaian dilakukan mempengaruhi sistem lainnya
T10 Concurrency | 1 | 3 | 3 | User Konkuren, Waktu peak bisa 1000 transaction per second
T11 Special Security Features | 1 | 2 | 2 | Pembagian hak akses dan role menyesuaikan apps manager
T12 Provides Direct Access for Third Parties | 1 | 1 | 1 | API
T13 Special User Training Facilities Are Required | 1 | 1 | 1 | Tidak memerlukan fasilitas khusus
Sum |  |  | 26.5
Complexity Factor |  |  | 0.6
C2 |  |  | 0.01
TCF = 0.6 + (0.01 x Total TCF Value) |  |  | 0.865
Environmental Factor | Weight | Impact 0-5 | Score | Keterangan
E1 Familiarity with System Development Process | 1.5 | 4 | 6 | Familiar
E2 Part-Time Workers | -1 | 0 | 0 | Tidak ada part-time
E3 Analyst Capability | 0.5 | 4 | 2 | Memiliki kemampuan analisis sistem yang baik
E4 Application Experience | 0.5 | 4 | 2 | Berpengalaman mengembangkan aplikasi
E5 Object-Oriented Experience | 1 | 4 | 4 | Berpengalaman dengan object oriented
E6 Motivation | 1 | 4 | 4 | Dukungan yang baik dari organisasi
E7 Difficult Programming Language | -1 | 3 | -3 | Bahasa pemrograman Baru
E8 Stable Requirements | 2 | 3 | 6 | Kebutuhan tidak berubah
Sum (ETF) |  |  | 21
ECF = 1.4 +(-0.03 * Environmental Total Factor) |  |  | 0.77
PF (Historical based average man hours per use case point) |  |  | 12

## Use Case Point Per Paket
Perhitungan Effort CEISACARE 2023
No | Sub Paket | Total UAW | Total UUCW | UUCP (UAW+UUCW) | UCP (UUCP*TCF*EF) | PHM (UCP * 20) | WD (PHM/8) | MM (WD/22)
1 | CEISACARE | 15 | 295 | 310 | 207.669 | 4153.38 | 519.1725 | 23.5987
2
| Total | [6 empty] | 23.5987
Keterangan
| UAW = Unadjusted Actor Weighting |  |  |  | 198 | 1623.6 | 1.623
| UUCW = Unadjusted Use Case Weighting |  |  |  | 139.5 | 1143.9 | 1.144 man-hour (orang per jam)
UUCP = Unadjusted Use Case Point
UCP = Use Case Point
PHM = Person-Hours Multiplier
WD = Working Days
MM = Man-Month
| Person-Hours Multiplier (PHM) | Value
| Decision rule: 20 or 28 hours | 20

## Cost Estimation Per Paket
Cost Estimation by Use Case | [6 empty] | Planning (Actual) | Analysis | Design | Implementation
[7 empty] | 15 | 20 | 35 | 30
KAK Akhir Tahun | [6 empty] | OPSI 1
Phase | Prosentase Effort Distribution | Effort Distribution (Man-Month) | PIC | Gaji Per Bulan (Inkindo, 2023) | Cost Estimation |  | MM | Role | Effort Distribution (Man-Month) | Waktu | Kebutuhan | Tersedia | Gap
Software Phase Development | [7 empty] | PM | 0.912 | 0.076 | 0 | 6 | 6
Needs analysis (Requirement) | 1.6 | 0.384 | Business Analyst | 21950000 | 8428800 | ba | 24 | BA | 0.384 | 0.032 | 0 | 8 | 8
Specification | 7.5 | 1.8 | System Analyst | 21950000 | 39510000 | sa |  | SA | 5.592 | 0.466 | 0 | 19 | 19
Design | 6 | 1.44 | System Analyst | 21950000 | 31608000 | sa | Bulan | PROG | 12.48 | 1.04 | 1 | 28 | 27
Implementation (Coding) | 52 | 12.48 | Programmer | 21950000 | 273936000 | p | 12 | QC | 2.16 | 0.18 | 0 | 8 | 8
Acceptance & installation | 5.5 | 1.32 | System Analyst | 21950000 | 28974000 | sa |  | QA | 0.216 | 0.018 | 0 | 3 | 3
Ongoing life-cycle activity |  | 0 | [5 empty] | TW | 2.256 | 0.188 | 0 | 0 | 0
Project management | 3.8 | 0.912 | Project Manager | 28150000 | 25672800 | pm |  |  | 24 |  | 1 | 72 | 71
Configuration management | 4.3 | 1.032 | System Analyst | 25050000 | 25851600 | sa
Documentation | 8.4 | 2.016 | Tehnical Writer | 13950000 | 28123200 | tw |  | Tingkat produktivitas
Training & technical support | 1 | 0.24 | Tehnical Writer | 13950000 | 3348000 | tw |  | Role | Tingkatan | Rata - rata
Quality and testing phases |  | 0 | [5 empty] | PM | 0.10 - 0.15 | 0.125
Integrated testing | 7 | 1.68 | Tester | 13950000 | 23436000 | qc |  | BA | 0.15 - 0.20 | 0.175
Quality assurance | 0.9 | 0.216 | Tester | 13950000 | 3013200 | qa |  | SA | 0.20 - 0.30 | 0.25
Evaluation & testing | 2 | 0.48 | Tester | 13950000 | 6696000 | qc |  | PROG | 0.25 - 0.35 | 0.3
Total of Effort | 100 | 24 |  |  | 498597600 |  | 498597600 | QC | 0.15 - 0.20 | 0.175 |  | 2.4
Estimasi Garansi 25% |  |  |  |  | 124649400 |  |  | QA | 0.15 - 0.20 | 0.175
Sub Total |  |  |  |  | 623247000 |  |  | TW | 0.10 - 0.15 | 0.125
PPN 11% |  |  |  |  | 68557170
Total |  |  |  |  | 691804170
[8 empty] | Phase | Prosentase Effort Distribution | PIC
Software Phase Development
[8 empty] | Needs analysis (Requirement) | 1.6 | Business Analyst
[8 empty] | Specification | 7.5 | System Analyst
[8 empty] | Design | 6 | System Analyst
[8 empty] | Implementation (Coding) | 52 | Programmer
[8 empty] | Acceptance & installation | 5.5 | System Analyst
Ongoing life-cycle activity
[8 empty] | Project management | 3.8 | Project Manager
[8 empty] | Configuration management | 4.3 | System Analyst
[8 empty] | Documentation | 8.4 | Tehnical Writer
[8 empty] | Training & technical support | 1 | Tehnical Writer
Quality and testing phases
[8 empty] | Integrated testing | 7 | Tester
[8 empty] | Quality assurance | 0.9 | Tester
[8 empty] | Evaluation & testing | 2 | Tester